## Sheet1
Task | Phase | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  | July
|  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Preparation phase report | Preparation | bar: February 1 to February 4
Preparation phase preparation | Preparation | bar: February 1 to February 4
Build data ingest pipeline | Infrastrucutre
Build data transformation pipeline | Infrastructure
Build model building pipeline | Infrastructure
Module integration | Infrastructure
Hyperparameter optimization setup | Infrastructure
Parelellization of RL and Deep Learning | Infrastructure
Initial model training | Training | bar: March 3 to May 4
Bug fixing and result verification | Training | bar: March 3 to May 4
Hyperparameter optimization | Training | bar: March 3 to May 4
Final training | Training | bar: March 3 to May 4
First draft of thesis | Report Writing | bar: May 1 to July 1
Second draft of thesis | Report Writing | bar: May 1 to July 1
Final draft of thesis | Report Writing | bar: May 1 to July 1
Thesis defense preparation | Defense | bar: July 1 to July 4